**Service Contract Change Order**

Service: Covid 19 Security at High Rises

Contract No.: 20-021

Contractor: **North East Security Solutions**

Change Order Title: Time Extension, Additional 61 days and Costs Associated with Time Extension

Change Order #: **CO-003**

Change Order Date: July 20, 2020

In connection with the Providence Housing Authority’s (hereto referred to as “The Authority”) **Contract No. 20-021** a change is being ordered in accordance with **Article 4- Time of Performance** and **Article 2-The Contract Price**

Change Order Number Three {003} shall extend the duration of the original contract.

Change Order Number Three {003} shall authorized additional contract price associated with time extension.

**Time Extension:**

Original Start Date: March 18, 2020

Original End Date: April 18, 2020

Change Order Two End Date: July 31, 2020

**Change Order Three Additional Time: 61 Days**

**Change Order Three End Date: September 30, 2020**

Vendor shall continue to perform existing duties as described in contract Article 1- Statement of Work, Contract number 20-021.

Revised Costs to Service Contract Number 20-021 as a result of the **change orders to date** is as follows:

|  |  |
| --- | --- |
| **ORIGINAL CONTRACT SUM ……………………………………………………….** | **$43,680.00**  |
|  |  |
| CHANGE ORDER NUMBER ONE ……………………….…….…….…….…….… | $67,860.00 |
| CHANGE ORDER NUMBER TWO ……………………….…….…….…….…….  | $91,260.00 |
| **CHANGE ORDER NUMBER THREE ……………………….…….…….……….**  | **$93,600.00** |
| **NEW CONTRACT SUM TO DATE …………………………………………………** | **$296,400.00** |